## Sheet1
Date | Task / Experiment Section | Target Molecule
Jan 1, 2025 | Literature review – collection of aptamer studies for opioids (Fentanyl, Oxycodone, Tramadol, Codeine, Methadone) | —
Jan 15, 2025 | Retrieval and curation of Fentanyl original aptamer sequences (FEN1–FEN8) from literature | Fentanyl (Original)
Feb 1, 2025 | Secondary structure prediction using Mfold/RNAfold; analysis of stem–loop regions, GC% | Fentanyl (Original)
Feb 15, 2025 | Tertiary structure modelling and optimization using 3dRNA/DNA web server | Fentanyl (Original)
Mar 1, 2025 | Docking setup and baseline docking (LibDock) for FEN1–FEN8 | Fentanyl (Original)
Mar 15, 2025 | Docking analysis and thermodynamic interpretation (ΔG, LibDock scores, interaction mapping) | Fentanyl (Original)
Mar 30, 2025 | Truncation and point-mutation design for best Fentanyl aptamer (FEN8; residues 28–29 etc.) | Fentanyl (Mutant Design)
Apr 15, 2025 | Docking of mutated Fentanyl aptamers (FEN8_1–FEN8_15); thermodynamic and interaction comparison | Fentanyl (Mutated)
Apr 30, 2025 | In-silico modification study — thiol/amine/biotin/FITC modifications at 5′/3′ ends; structural optimization, FRET-pair validation, docking setup | Modified Aptamers (primarily Fentanyl)
May 15, 2025 | Retrieval and curation of Oxycodone original aptamer sequences (OM1–OM36) | Oxycodone (Original)
May 30, 2025 | Secondary & tertiary structure prediction for Oxycodone aptamers; identification of lead OM16 | Oxycodone (Original)
Jun 15, 2025 | Mutation and docking analysis of OM16 (mutants OM16_1–OM16_15) | Oxycodone (Mutated)
Jun 30, 2025 | Retrieval of Tramadol aptamer (TR_OG/APT39); secondary and tertiary structure modelling | Tramadol (Original)
Jul 15, 2025 | Docking and mutation study of Tramadol (APT39; residues 40–41; TR1–TR15) | Tramadol (Mutated)
Jul 30, 2025 | Retrieval and structural prediction of Codeine aptamers (FC5, FC45) | Codeine (Original)
Aug 15, 2025 | Docking, thermodynamics, and comparative analysis across all targets (ΔG, LibDock, heatmaps, interaction summaries); final documentation | Cross-target comparison